Work Breakdown Structure

Table 2. Work Breakdown Structure

| ID | DESCRIPTION | (days) | RESOURCES | START DATE | END DATE |
| --- | --- | --- | --- | --- | --- |
| 1 | PLANNING PHASE | 51 |  | 12/01/2025 | 01/20/2026 |
| 1.1 | Client Identification and Coordination | 10 |  | 12/01/2025 | 12/10/2025 |
| 1.2 | Define Project Title | 5 |  | 12/11/2025 | 12/15/2025 |
| 1.3 | Conduct Project Analysis | 10 |  | 12/16/2025 | 12/25/2025 |
| 1.3.1 | Define project scope and objectives | 3 | Project Manager, System Analyst. | 12/16/2025 | 12/18/2025 |
| 1.3.2 | Outline project requirements and deliverables | 3 | Project Manager, System Analyst. | 12/19/2025 | 12/21/2025 |
| 1.3.3 | Identify project stakeholders and their roles | 2 | Project Manager, System Analyst | 12/22/2025 | 12/23/2025 |
| 1.3.4 | Develop project communication and risk management strategies | 2 | Project Manager, System Analyst | 12/24/2025 | 12/25/2025 |
| 1.4 | Project Budget and Costing | 15 |  | 12/26/2025 | 01/09/2026 |
| 1.4.1 | Determine project cost (software, tools, resources) | 5 | Project Manager | 12/26/2025 | 12/30/2025 |
| 1.4.2 | Estimate project timeline and resource requirements | 5 | Project Manager | 12/31/2025 | 01/04/2026 |
| 1.4.3 | Calculate budget breakdown (operational and administrative) | 5 | Project Manager | 01/05/2026 | 01/09/2026. |
| 1.5 | Risk Management Plan | 11 |  | 01/10/2026 | 01/20/2026 |
| 1.5.1 | Identify potential risks and impacts | 3 | Project Manager, System Analyst. | 01/10/26 | 01/12/26 |
| 1.5.2 | Evaluate risk likelihood and consequences | 4 | Project Manager, System Analyst. | 01/13/2026 | 01/16/2026 |
| 1.5.3 | Develop mitigation strategies and contingency plans | 4 | Project Manager. | 01/17/2026 | 01/20/2026 |
| 2.0 | DESIGN PHASE | 72 |  | 01/24/2026 | 04/05/2026 |
| 2.1 | System Architecture Design | 20 |  | 01/24/2026 | 02/12/2026 |
| 2.1.1 | Develop detailed system architecture blueprint | 7 | System Analyst | 01/24/2026 | 01/30/2026 |
| 2.1.2 | Define system components | 7 | System Analyst | 01/31/2026 | 02/06/26 |
| 2.1.3 | Outline data flow and processing mechanisms | 6 | System Analyst, Programmer | 02/07/2026 | 02/12/2026 |
| 2.2 | Database Design | 25 |  | 02/13/2026 | 03/09/2026 |
| 2.2.1 | Design database schema | 8 | System Analyst | 02/13/2026 | 02/20/2026 |
| 2.2.2 | Develop physical database design | 10 | Programmer | 02/21/2026 | 03/02/2026 |
| 2.2.3 | Define data integrity and referential constraints | 7 | Programmer | 03/03/2026 | 03/09/2026 |
| 2.3 | UI and UX Design | 27 |  | 03/10/2026 | 04/05/2026 |
| 2.3.1 | Create wireframes for system user interface | 10 | System Analyst | 03/10/2026 | 03/19/2026 |
| 2.3.2 | Design user-friendly navigation and layout | 10 | System Analyst, Programmer | 03/20/2026 | 03/29/2026 |
| 2.3.3 | Review and finalize UI/UX design | 7 | Project Manager, System Analyst | 03/30/2026 | 04/05/2026 |
| 3.0 | Development Phase | 136 |  | 04/09/2026 | 08/22/2026 |
| 3.1 | Database Development | 30 |  | 04/09/2026 | 05/08/2026 |
| 3.1.1 | Develop and deploy database schema | 10 | Programmer | 04/09/2026 | 04/18/2026 |
| 3.1.2 | Implement data integrity and constraint | 10 | Programmer | 04/19/2026 | 04/28/2026 |
| 3.1.3 | Create stored procedures | 10 | Programmer | 04/29/26 | 05/08/2026 |
| 3.2 | Front-End Development | 35 |  | 05/09/2026 | 06/12/2026 |
| 3.2.1 | Develop user interface | 18 | Programmer | 05/09/2026 | 05/26/2026 |
| 3.2.2 | Implement responsive design and navigation | 17 | Programmer | 05/27/2026 | 06/12/2026 |
| 3.3 | Back-End Development | 45 |  | 06/13/2026 | 07/27/2026 |
| 3.3.1 | Develop server-side system | 12 | Programmer | 06/13/2026 | 06/24/2026 |
| 3.3.2 | Implement business logic, data validation, and security | 11 | Programmer, System Analyst | 06/25/2026 | 07/05/2026 |
| 3.3.3 | Connect system with database | 10 | Programmer. | 07/06/2026 | 07/15/2026 |
| 3.3.4 | Implement user authentication and role-based access | 12 | Programmer | 07/16/2026 | 07/27/2026 |
| 3.4 | System Integration | 26 |  | 07/28/2026 | 08/22/2026 |
| 3.4.1 | Integrate front-end and back-end components | 13 | Programmer | 07/28/2026 | 08/09/2026 |
| 3.4.2 | Ensure proper data flow and system functionality | 13 | Programmer, System Analyst | 08/10/2026 | 08/22/2026 |
| 4.0 | TESTING PHASE | 32 |  | 08/24/2026 | 09/24/2026 |
| 4.1 | Unit Testing | 10 |  | 08/24/2026 | 09/02/2026 |
| 4.1.1 | Develop unit test cases | 4 | Programmer | 08/24/2026 | 08/27/2026 |
| 4.1.2 | Execute unit tests and validate functionality | 4 | Programmer | 08/28/2026 | 08/31/2026 |
| 4.1.3 | Identify and fix bugs or errors | 2 | Programmer, System Analyst | 09/01/2026 | 09/02/2026 |
| 4.2 | Integration Testing | 11 |  | 09/03/2026 | 09/13/2026 |
| 4.2.1 | Develop integration test scenarios | 5 | System Analyst | 09/03/2026 | 09/07/2026 |
| 4.2.2 | Execute integration tests | 3 | Programmer, System Analyst | 09/08/2026 | 09/10/2026 |
| 4.2.3 | Identify and fix integration issues | 3 | Programmer | 09/11/2026 | 09/13/2026 |
| 4.3 | System Testing | 11 |  | 09/14/2026 | 09/24/2026 |
| 4.3.1 | Conduct system-wide testing | 4 | System Analyst, Programmer | 09/14/2026 | 09/17/2026 |
| 4.3.2 | Verify compliance with project requirements | 4 | System Analyst, Programmer | 09/18/2026 | 09/21/2026 |
| 4.3.3 | Identify and resolve remaining issues | 3 | Programmer. | 09/22/2026 | 09/24/2026 |
| 5.0 | DEPLOYMENT PHASE | 9 |  | 10/01/2026 | 10/09/2026 |
| 5.1 | Database Deployment | 3 |  | 10/01/2026 | 10/03/2026 |
| 5.1.1 | Deploy database schema | 1 | Programmer | 10/01/2026 | 10/01/2026 |
| 5.1.2 | Deploy database in live environment | 2 | Programmer | 10/02/2026 | 10/03/2026 |
| 5.2 | System Deployment | 3 |  | 10/04/2026 | 10/06/2026 |
| 5.2.1 | Deploy back-end system | 1 | Programmer. | 10/04/2026 | 10/04/2026 |
| 5.2.2 | Deploy front-end on web server | 1 | Programmer. | 10/05/2026 | 10/05/2026 |
| 5.2.3 | Configure system settings and connections | 1 | Programmer, System Analyst | 10/06/2026 | 10/06/2026 |
| 5.3 | Deployment Verification | 3 |  | 10/07/2026 | 10/09/2026 |
| 5.3.1 | Perform final system checks | 2 | System Analyst, Programmer | 10/07/2026 | 10/08/2026 |
| 5.3.2 | Ensure system accessibility and functionality | 1 | System Analyst | 10/09/2026 | 10/09/2026 |
| 6.0 | REVIEW PHASE | 8 |  | 10/10/2026 | 10/17/2026 |
| 6.1 | System Performance Monitoring | 3 |  | 10/10/2026 | 10/12/2026 |
| 6.1.1 | Monitor system performance and stability | 2 | System Analyst. | 10/10/2026 | 10/11/2026 |
| 6.1.2 | Identify areas for improvement | 1 | System Analyst, Programmer. | 10/12/2026 | 10/12/2026 |
| 6.2 | Security, Logging, and Maintenance | 3 |  | 10/13/2026 | 10/15/2026 |
| 6.2.1 | Implement logging and error handling | 1 | Programmer | 10/13/2026 | 10/13/2026 |
| 6.2.2 | Monitor system security | 1 | System Analyst. | 10/14/2026 | 10/14/2026 |
| 6.2.3 | Perform regular backups and maintenance | 1 | Programmer | 10/15/2026 | 10/15/2026 |
| 6.3 | Security Monitoring Updates | 2 |  | 10/16/2026 | 10/17/2026 |
| 6.3.1 | Develop and implement security measures | 1 | Programmer | 10/16/2026 | 10/16/2026 |
| 6.3.2 | Regularly monitor system security | 1 | System Analyst | 10/17/2026 | 10/17/2026 |
| 7 | LAUNCH PHASE | 12 |  | 10/19/2026 | 10/30/2026 |
| 7.1 | Set up training programs | 3 |  | 10/19/2026 | 10/21/2026 |
| 7.1.1 | Conduct training for end-users, administrators, and support personnel | 3 | System Analyst, Technical Writer. | 10/19/2026 | 10/21/2026 |
| 7.2 | Support and Troubleshooting | 4 |  | 10/22/2026 | 10/25/2026 |
| 7.2.1 | Provide ongoing technical support to users and administrator | 4 | Programmer, System Analyst | 10/22/2026 | 10/25/2026 |
| 7.3 | Manage feedback and Continuous Improvement | 5 |  | 10/26/2026 | 10/30/2026 |
| 7.3.1 | Collect user feedback and feature requests | 1 | System Analyst, Technical Writer | 10/26/2026 | 10/26/2026 |
| 7.3.2 | Implement necessary enhancements | 2 | Programmer, Technical Writer | 10/27/2026 | 10/28/2026 |
| 7.3.3 | Prepare final documentation and reports | 2 | Project Manager, Technical Writer | 10/29/2026 | 10/30/206 |
|  | TOTAL WORKING DAYS | 320 |  | 12/01/2025 | 11/30/2026 |